## Work packages
ID | Subject | Type | Status | Created on | Finish date | Work | Spent time | Assignee | Priority | Story Points | Project | Description
22931 | [W52RE][Platform][UAT][UI][Credit Card Limit Rearrange] Need to show Service Charge, VAT, Fee & Grand Total on credit card limit rearrange page | Bug | Closed | 12/03/2024 12:06 PM | 12/10/2024 |  | 0.2 | Abir Hossain | Normal |  | NCC IB & Wallet | [https://prnt.sc/0KN4\_BIH1YuE](https://prnt.sc/0KN4_BIH1YuE)
22935 | [Service Request]On Credit card limit rearrangement request view page showing only "Charge Amount" | Bug | Closed | 12/03/2024 12:21 PM | 12/09/2024 | 0.5h | 0.5 | Mostafijur Rahman | Normal |  | NCC IB & Wallet | [https://prnt.sc/kxN0dwRCyw9i](https://prnt.sc/kxN0dwRCyw9i)
22941 | [W52RE][App][DEV][API][Demand Draft] Need to show Service Charge, VAT, Fee & Grand Total on Request Demand Draft page | Bug | Closed | 12/03/2024 02:22 PM | 12/10/2024 |  | 0.2 | Abir Hossain | Normal |  | NCC IB & Wallet | [https://prnt.sc/xUVJwy4dQiC2](https://prnt.sc/xUVJwy4dQiC2)
23076 | [W52RE][App][Dev][UI][Positive Pay] Initiate Data isn't showing In Service Request History | Bug | Closed | 12/04/2024 12:44 PM | 12/03/2024 |  | 0.25 | Abir Hossain | Normal |  | NCC IB & Wallet | **Reproduce:** 1. Step 1: Submit any Service Request 2. Step 2: Check in Service Request History
23387 | [Admin][Local][Bulk Push Notification] - Width of the "Message Text" column should be more wider. Contents are cramped on the column | Bug | Closed | 12/09/2024 11:30 AM | 12/19/2024 |  | 0.25 | Md Mehedi Hasan Arif | High |  | NCC IB & Wallet | **Expected Result:** The width of the "Message Text" column is too narrow and Contents are cramped on the column. It should be wider and also user friendly for the user. **screenshot:** [****](https://prnt.sc/cIKOckEeoYqW)
23388 | [Admin][Local][Bulk Push Notification] - Width of the "Banner Text" & "Linked Url" column should be adjusted. If user enters the maximum character limit the Index page gets broken | Bug | Closed | 12/09/2024 11:33 AM | 12/19/2024 |  | 0.5 | Md Mehedi Hasan Arif | High |  | NCC IB & Wallet | **Expected Result:** Width of the "Banner Text" &amp; "Linked Url" column should be adjusted. If user enters the maximum character limit the Index page gets broken. The writings on the column should be wrapped on the column.
23390 | [Admin][Local][Bulk Push Notification] - Character Limit validation message should be changed. Expected ,essage should be "Character limit exceeded. Max: 25" | Bug | Closed | 12/09/2024 11:40 AM | 12/19/2024 |  | 0.25 | Md Mehedi Hasan Arif | High |  | NCC IB & Wallet | **Expected Result:** Character Limit validation message should be changed. Expected ,essage should be **"Character limit exceeded. Max: 25"** ****
23393 | [Admin][Local][Bulk Push Notification] - Test Subscription feature is not functionl, no notification is sent to the designated user | Bug | Closed | 12/09/2024 11:50 AM | 12/19/2024 |  | 0.0 | MD Sadman Sakib | High |  | NCC IB & Wallet | **Expected Result:** Test Subscription feature is not functional, no notification is sent to the designated user.
23394 | [Admin][Local][Bulk Push Notification] - Push notification is not functional, no notification received on customer's end | Bug | Closed | 12/09/2024 11:51 AM | 12/19/2024 |  | 2.0 | Md. Shakhawat Hossain | High |  | NCC IB & Wallet | **Expected Result: Push notification is not functional, no notification received on customer's end**
23460 | [Within FT] On the status page timestamp is showing in UTC | Bug | Closed | 12/10/2024 09:38 AM | 12/12/2024 | 0.5h | 1.0 | MD Sadman Sakib | Normal |  | NCC IB & Wallet | [https://prnt.sc/LIj9Zv69Ql57](https://prnt.sc/LIj9Zv69Ql57)
23554 | [Web][Local][TopUp] Full Button Name cut of on Final Page in Small Screen | Bug | Closed | 12/11/2024 10:23 AM | 12/12/2024 | 1h | 1.0 | Labeba Tahsin | High |  | NCC IB & Wallet | **EnvironmentEnvironment:** Local **Browser:** Chrome **Platform:** Web **Steps to Reproduce:** * Go to the Sidebar or Dashboard * Click on the **TopUp** * Do a transaction * Go to the Final page **Actual Result:** Full Button Name cut off on Final Page in Small Screen **ScreenShot:** https://prnt.sc/tcMfiuUcxtFY **Expected Result:** Should show Full button
23636 | [Customer][Activity Log] - (Login/Top Up)'s Activity Log shows future date | Bug | Closed | 12/12/2024 12:02 PM | 12/19/2024 |  | 0.0 | Md. Abdullah Al Noman | High |  | NCC IB & Wallet | **Environment:** Local **Expected Result:** Activity time for Log in should show exact time when customer logged in to the system. However, system is showing future time for Login. **Screenshot:**
23726 | [ServiceRequest][Stop Cheque] Success page showing wrong data | Bug | Closed | 12/15/2024 02:47 PM | 12/31/2024 | 0.5h | 0.5 | Md. Shakhawat Hossain | Normal |  | NCC IB & Wallet | Steps: 1. Initiate a stop cheque request 2. In the success page, observe that 'Reason' and 'Cheque No' data are exchanged. (Reason field is showing cheque no and vice-versa) Screenshot: https://prnt.sc/eweOmQcGeouK
23727 | [ServiceRequest][Stop Cheque] Stop Cheque history is not showing in service request history | Bug | Closed | 12/15/2024 02:55 PM | 12/18/2024 |  | 1.5 | Md. Shakhawat Hossain | Normal |  | NCC IB & Wallet | Steps: 1. Initiate a stop cheque request 2. Go to service request history and select 'Stop Cheque' from dropdown 3. Observe Stop Cheque history not showing Screenshot: https://prnt.sc/yjlUmJis6\_cl
23731 | [Admin] [ServiceRequest] User can select 'To Date' less than 'From Date' | Bug | Closed | 12/15/2024 03:27 PM | 01/12/2025 | 4h | 5.0 | Md Mehedi Hasan Arif | Normal |  | NCC IB & Wallet | Steps: 1. Go Service Request &gt; Stop Cheque request 2. Observe that 'To Date'can be selected less than 'From Date' Screenshot: https://prnt.sc/fz5SyeHMoZM\_
23733 | [Admin][ServiceRequest] Filter with 'Status' not working | Bug | Closed | 12/15/2024 03:31 PM | 12/15/2024 |  | 1.0 | Pronab Kumar Halder | Normal |  | NCC IB & Wallet | Steps: 1. Go Service Request &gt; Stop Cheque request 2. Search by Status 3. Observe that filtering not working
23735 | [App][ServiceRequest] Service request history data not showing for all service request | Bug | Closed | 12/15/2024 03:34 PM | 12/18/2024 | 1h | 1.0 | Mostafijur Rahman | Normal |  | NCC IB & Wallet | Steps: 1. Go Service Request history 2. Observe that no data showing
23738 | [Admin][ServiceRequest][Stop Cheque] During request status change, if admin user does not input remarks, system navigates to the previous page | Bug | Closed | 12/15/2024 03:56 PM | 12/15/2024 |  | 0.5 | Md Mehedi Hasan Arif | Normal |  | NCC IB & Wallet | Steps: 1. Go Service Request &gt; Stop Cheque request 2. Go to details view 3. Select updated status 4. Click on 'Uodate' button without inputting remarks 5. Observe system navigates to the previous page
23739 | [App][ServiceRequest] After changing reuest status from admin panel, user does not get notification | Bug | Closed | 12/15/2024 04:02 PM | 12/15/2024 |  | 0.5 | Md. Shakhawat Hossain | Normal |  | NCC IB & Wallet | Steps: 1. Initiate a stop cheque request 2. Approve from admin panel 3. Observe user doesn't get notification
23798 | [ServiceRequest]Account E-Statement, Card Limit Transfer Request > Success Page > Showing 'Transaction Initiated' | Bug | Closed | 12/17/2024 10:36 AM | 12/17/2024 |  | 0.0 | Md. Shakhawat Hossain | Normal |  | NCC IB & Wallet | Steps: 1. Go to Account Service&gt; Account E-Statement 2. Request for e-statement 3. Observe that in success page, showing 'Transaction is initiated' but it is not a transaction. Screenshot: https://prnt.sc/DpzStnxRC9ib
23802 | [Admin][ServiceRequest][Account E-Statement] Showing internal service exception while filtering with 'All' Status | Bug | Closed | 12/17/2024 10:51 AM | 12/17/2024 |  | 1.0 | Pronab Kumar Halder | Normal |  | NCC IB & Wallet | Steps: 1. Service Reuest History &gt; Account eStatement 2. Filter by Status "All" 3. Observe the error Screenshot: https://prnt.sc/-Sdoarw8N2mu
23823 | [App][ServiceRequest][Credit Card Limit Transfer] Review Page > Amount, Charge, Fee, Grand Total Fields are not required for service request | Bug | Closed | 12/17/2024 12:58 PM | 12/17/2024 |  | 0.0 | Md. Shakhawat Hossain | Normal |  | NCC IB & Wallet | Steps: 1. Service Reuest History &gt; Card Limit Transfer 2. Go to review page 3. Observe that there are amount, fee, service charge, VAT, Grand Total fields are present. These fields are not required as user is not doing any transaction. It's a service request Screenshot: https://prnt.sc/4wCv8NzKxCr0
23871 | [W52RE][Admin][UAT][UI][ServiceRequest] In E-commerce Txn Block/unblock, Filter with "Status" isn't working | Bug | Closed | 12/17/2024 06:01 PM | 12/18/2024 | 1.5h | 1.5 | Mostafijur Rahman | Normal |  | NCC IB & Wallet | [https://prnt.sc/2oMsStdyIsLG](https://prnt.sc/2oMsStdyIsLG)
23873 | [App][UAT][API][ServiceRequest] E-commerce Txn Block/unblock- Not getting any push notification after request submit, approve or rejection | Bug | Closed | 12/17/2024 06:07 PM | 12/29/2024 | 2h | 3.0 | MD Sadman Sakib | Normal |  | NCC IB & Wallet
24049 | [Web][UAT][MFS][W52R2] Full Button Name cut off on Final Page in Small Screen | Bug | Closed | 12/18/2024 01:08 PM | 12/22/2024 | 1h | 0.0 | Sharif Hossen | High |  | NCC IB & Wallet | **Applicable for Notification -&gt; Details** **Environment:** UAT **Browser:** Chrome **Platform:** Web **Steps to Reproduce:** * Go to the Sidebar or Dashboard * Click on the **MFS Fund Transfer** * Do a Transaction * Now observe the Final page **Actual Result:** Full Button Name cut off on Final Page in Small Screen **ScreenShot:** [https://prnt.sc/unKRPt6ndk0x](https://prnt.sc/unKRPt6ndk0x) **Expected Result:** Should show Full button
24090 | [Web][UAT][W52R2][MFS] [Remove Beneficiary] The user not getting any SMS and email for Remove Beneficiary | Bug | Closed | 12/18/2024 05:05 PM | 12/19/2024 |  | 1.0 | MD Sadman Sakib | High |  | NCC IB & Wallet | **Environment:** UAT **Browser:** Chrome **Platform:** Web **Steps to Reproduce:** * Go to the Sidebar or Dashboard * Click on the **MFS Fund Transfer** * Remove a Beneficiary from the Beneficiary list **Actual Result:** The user is not getting any SMS and email for Remove Beneficiary **Expected Result:** The user should receive SMS &amp; Email
24219 | [WEB][W52R2][Customer][Dashboard] - Discrepancy between Shortcuts on WEB and Mobile APP | Bug | Closed | 12/19/2024 11:39 AM | 12/23/2024 | 0.5h | 0.5 | Sharif Hossen | Normal |  | NCC IB & Wallet | #### Environment: UAT #### Expected Result: Shortcut icons on the dashboard should be similar to mobile APP
24221 | [App][UI][ServiceRequest][Loan Request] Error message issue | Bug | Closed | 12/19/2024 11:45 AM | 12/17/2024 |  | 0.5 | Mainul Karim | Normal |  | NCC IB & Wallet | Steps: 1. Go to Card Services &gt; Loan Request 2. Input amount more than unused limit 3. App showing an error message Issue: 1. All the words start with a capital letter. Expecting only the first word of the sentence should start with capital letter 2. There is an extra space after the 'than' word. Remove the extra space Screenshot:
24222 | [App][UI][ServiceRequest][Loan Request] Transfer Amount field should be 'Loan Amount' | Bug | Closed | 12/19/2024 11:47 AM | 12/17/2024 |  | 1.0 | Mainul Karim | Normal |  | NCC IB & Wallet | Steps: 1. Go to Card Services &gt; Loan Request 2. There is a field called 'Transfer Amount'. It should be 'Loan Amount' Screenshot:
24225 | [App][UI][ServiceRequest][Loan Request] Loan Summary page issues | Bug | Closed | 12/19/2024 12:00 PM | 12/17/2024 |  | 0.5 | Emam Hasan Bijoy | Normal |  | NCC IB & Wallet | Steps: 1. Go to Card Services &gt; Loan Request 2. Go to loan summary page Issue: 1. Type should be 'Loan Request' 2. Tenor is showing twice. Remove 'Tenor Month' field 3. To Account field label should be 'Disbursement Account' 4. % sign missing in interest rate 5. Loan Amount field is missing 6. Installment Amount is calculated based on the 'Base Amount', it should be calculated on loan amount 7. What is necessary of 'Service Charge', 'VAT', 'Amount', Grans Total' fields in loan request summary page Screenshot:
24227 | [App][UI][ServiceRequest][Loan Request] Success page only showing card number | Bug | Closed | 12/19/2024 12:16 PM | 12/30/2024 |  | 1.5 | Emam Hasan Bijoy | Normal |  | NCC IB & Wallet | Steps: 1. Go to Card Services &gt; Loan Request 2. Do a loan request 3. Observe that in the success page, only card number and product type showing. Other information should show Screenshot:
24230 | [App][UI][ServiceRequest][Loan Request] After resending OTP, 'Your OTP expires' message still exists | Bug | Rejected | 12/19/2024 12:43 PM | 12/17/2024 |  | 0.0 | Md. Shakhawat Hossain | Normal |  | NCC IB & Wallet | Steps: 1. Go to Card Services &gt; Loan Request 2. Do a loan request 3. Send OTP 4. Wait for the OTP expiration time 5. After the time ends, app shows a message "Your OTP expires' 6. Click on Resend OTP 7. Observe that 'Your OTP expires' message still exists Screenshot:
24241 | [App][UI][ServiceRequest][Loan Request] Admin requirements not implemented | Bug | Closed | 12/19/2024 01:11 PM | 12/17/2024 |  | 0.25 | Md. Shakhawat Hossain | Blocker |  | NCC IB & Wallet | Steps: 1. Login in amdin panel 2. Go to Service Reuest &gt; Loan Request from unused card limit Issues: 1. Observe that loan requests are not showing 2. Admin can not review or approve, reject, disburse loan
24271 | [App][UI][ServiceRequest][EMI Request] Customer is not receiving message with request ID | Bug | Closed | 12/19/2024 03:46 PM | 12/29/2024 |  | 2.0 | MD Sadman Sakib | High |  | NCC IB & Wallet | Steps: 1. Go to Card Services &gt; EMI Request 2. Do an EMI request 3. Observe user do no receive any message
24273 | [Admin][ServiceRequest][EMI Conversion Request] Showing internal service exception while filtering with date | Bug | Closed | 12/19/2024 03:56 PM | 12/17/2024 |  | 2.5 | Md. Mehedi Hasan | High |  | NCC IB & Wallet | Steps: 1. Service Reuest History &gt; EMI Conversion 2. Filter by date 3. Observe the error
24276 | [Admin][UI][ServiceRequest][EMI Request] Configure Eligible Transaction Types, Configure Interest Rates feature not available in admin portal | Bug | Closed | 12/19/2024 03:58 PM | 12/17/2024 |  | 0.5 | Pronab Kumar Halder | Blocker |  | NCC IB & Wallet
24277 | [Web][UAT][W52R2][Fund Transfer] Title mismatch on Transfer Review page | Bug | Closed | 12/19/2024 04:01 PM | 12/22/2024 | 0.9h | 0.9 | Labeba Tahsin | Normal |  | NCC IB & Wallet | **Environment:** UAT **Browser:** Chrome **Platform:** Web **Steps to Reproduce:** * Go to the Sidebar or Dashboard * Click on the **Fund Transfer** * Go to the **Own or Within or Other FT page** * Input valid data for all the required fields and click on the Next button * Now observe the title **Actual Result:** Title mismatch on Transfer Review page **Expected Result:** The title should be "Transfer Review"
24303 | [Admin][UAT][W52R2][Customer Profile limit] Cant update any Per Transaction Maximum Limit with valid amount | Bug | Closed | 12/19/2024 07:29 PM | 12/30/2024 | 2.5h | 2.75 | Md Mehedi Hasan Arif | Normal |  | NCC IB & Wallet | Steps to reproduce: 1. Go to Customer Profile limit 2. Click on edit icon from action 3. Try to update any Per Transaction Maximum limit
24393 | [App][Dev][Functional][ServiceRequest][Request Card Cheque] In the app, both the card number and debit account dropdown fields appear. | Bug | Closed | 12/22/2024 06:05 PM | 12/30/2024 |  | 0.25 | Abir Hossain | Normal |  | NCC IB & Wallet | **Expected**: The card number field (which automatically detects the card type as credit or debit per BRD) is expected. **Reference**: * App: [https://prnt.sc/JUs6MibjD94Y](https://prnt.sc/JUs6MibjD94Y) * BRD: https://prnt.sc/5O4mRv0gmflK
24399 | [App][Dev][UI][ServiceRequest][Request Card Cheque] On the Request Success page, the text title needs to be updated | Bug | Closed | 12/22/2024 06:34 PM | 12/22/2024 |  | 0.25 | Md. Shakhawat Hossain | Normal |  | NCC IB & Wallet | **Expected**: Update text from "Transaction is initiated" to "Request is initiated." **Reference**: https://prnt.sc/REm9qqjnMw9n
24401 | [App][Dev][UI][ServiceRequest][Request Card Cheque] The phone number is displayed on the Request Success page, even though no input field for it was implemented in the input form. | Bug | Closed | 12/22/2024 06:38 PM | 12/30/2024 |  | 0.25 | Abir Hossain | Normal |  | NCC IB & Wallet | **Expected**: Remove Phone Number field **Reference**: https://prnt.sc/uYrBQ\_lhccuc
24402 | [App][Dev][UI][ServiceRequest][Request Card Cheque] The Amount, Service Charge, VAT, Fee, and Grand Total fields should not be displayed on the Request Details page. | Bug | Rejected | 12/22/2024 06:43 PM | 12/22/2024 |  | 0.0 | Md. Shakhawat Hossain | Normal |  | NCC IB & Wallet | **Expected**: Remove **Amount, Service Charge, VAT, Fee, and Grand Total fields.** **Reference: https://prnt.sc/DDMWR75So8QA**
24403 | [App][Dev][UI][ServiceRequest][Request Card Cheque] Data on the Request Details page should be displayed in the correct order, synchronized with the previous page. | Bug | Closed | 12/22/2024 06:46 PM | 12/22/2024 |  | 1.0 | Mainul Karim | Normal |  | NCC IB & Wallet | **Expected**: Maintain the serial as: Division-&gt; District-&gt;Thana-&gt; Address **Reference**: **https://prnt.sc/donaz--X4w5R**
24404 | [App][Dev][Functional][ServiceRequest][Request Card Cheque] Requested data is not displaying in the Service Request History. | Bug | Closed | 12/22/2024 06:52 PM | 12/30/2024 |  | 0.25 | Md. Shakhawat Hossain | Normal |  | NCC IB & Wallet | **Reference**: https://prnt.sc/HWLNaRSfLXIk
24408 | [Admin][Dev][UI][ServiceRequest][Request Card Cheque] Rename the label names and menu options to match those in the app. | Bug | Closed | 12/22/2024 06:56 PM | 12/29/2024 |  | 1.5 | Md Mehedi Hasan Arif | Normal |  | NCC IB & Wallet | **Expected**: **CARD CHEQUEBOOK REQUEST** changes as **Request Card Cheque** **Reference**: https://prnt.sc/kniCgetm24Ro
24417 | [Admin][Dev][UI][ServiceRequest][Request Card Cheque] Card Type data should display as either "Debit" or "Credit". | Bug | Closed | 12/22/2024 07:01 PM | 12/29/2024 |  | 0.3 | Md Abdullah Al Mahmud | Normal |  | NCC IB & Wallet | **Reference**: https://prnt.sc/ETUlQxwSDH2S
24421 | [Admin][Dev][UI][ServiceRequest][Request Card Cheque] Remove redundant fields from the filter options. | Bug | Closed | 12/22/2024 07:05 PM | 12/31/2024 | 0.5h | 0.1 | Abir Hossain | Normal |  | NCC IB & Wallet | **Expected**: * Card Type should be Dropdown filed * Remove Product Type &amp; Phone Number filed **Reference**: https://prnt.sc/YNXa0Zly8yJm
24424 | [Admin][Dev][UI][ServiceRequest][Request Card Cheque] In the Service Request Details view page, the Delivery Address [Branch] is displaying as N/A for the Home Delivery option. | Bug | Closed | 12/22/2024 07:09 PM | 12/31/2024 | 0.5h | 0.5 | Mostafijur Rahman | Normal |  | NCC IB & Wallet | **Expected**: No need to show Delivery Address **Reference**: https://prnt.sc/4qgo9Slvoz4\_
24426 | [Admin][Dev][UI][ServiceRequest][Request Card Cheque] In the Service Request Details view page, the Delivery Addres is displaying as N/A for the Branch Delivery option. | Bug | Closed | 12/22/2024 07:13 PM | 12/29/2024 |  | 0.0 | Mostafijur Rahman | Normal |  | NCC IB & Wallet | **Expected**: No need to show **Delivery Address \[District\], Delivery Address \[Thana\], Delivery Address \[Address\]** **Reference**: https://prnt.sc/CJuqJqbU5Wek
24430 | [Admin][Dev][UI][ServiceRequest][Request Card Cheque] Notification/ Email isn't appear for Approve, Reject and Cancel status | Bug | Closed | 12/22/2024 07:36 PM | 12/31/2024 | 0.5h | 0.1 | Abir Hossain | Normal |  | NCC IB & Wallet
24529 | [Admin][Dev][UI][ServiceRequest][Card USD Block/Unblock] Action Type should be a dropdown | Bug | Closed | 12/23/2024 01:18 PM | 12/31/2024 |  | 0.5 | Abir Hossain | Normal |  | NCC IB & Wallet | Steps: 1. Go To Service Request &gt; **CARD USD PART BLOCK UNBLOCK REQUEST** 2. **Obser that Action Type is a input field. But it should be a dropdown with value "Block" and "Unblock"** **https://prnt.sc/-YAmebBYbnV9**
24530 | [Admin][Dev][UI][ServiceRequest][Card USD Block/Unblock] What is the necessary of Phone Number field in filter criteria | Bug | Closed | 12/23/2024 01:20 PM | 12/31/2024 |  | 0.1 | Abir Hossain | Normal |  | NCC IB & Wallet | Steps: 1. Go To Service Request &gt; **CARD USD PART BLOCK UNBLOCK REQUEST** 2. **Obser that there is a Phone Number field. But there is no such criteria to search with. Rather there should be a search option with "Request ID"** https://prnt.sc/\_owwty0OJdc1
24541 | [App][Functional][ServiceRequest][Card USD Block/Unblock] Same request can be sent twice | Bug | Closed | 12/23/2024 01:51 PM | 12/30/2024 |  | 0.1 | Abir Hossain | Normal |  | NCC IB & Wallet | Steps: 1. Login as user in app 2. Place a card USD block request for a card 3. Observe that user can placed USD block request fro the same card again although there is the same request pending.
24542 | [Admin][Dev][Functional][ServiceRequest][Card USD Block/Unblock] Notification/ Email isn't appear for submitting a request, Approve request, Reject request and Cancel reqquest | Bug | Closed | 12/23/2024 01:53 PM | 12/29/2024 |  | 1.0 | MD Sadman Sakib | Normal |  | NCC IB & Wallet
24543 | [Admin][Functional][ServiceRequest][Card USD Block/Unblock] "Configure Eligible Cards" not implemented as per requirements | Bug | Closed | 12/23/2024 01:58 PM | 01/05/2025 | 4h | 5.5 | Abir Hossain | Normal |  | NCC IB & Wallet
24549 | [App][Functional][ServiceRequest][Card Reissue Request] Card type[Credit/Devit) selection from dropdown wise data will appear but in Card dropdown filed appear card number in both Debit account filed | Bug | Rejected | 12/23/2024 02:20 PM | 12/30/2024 |  | 0.0 | Abir Hossain | Normal |  | NCC IB & Wallet | **Expected**: Card type \[Debit/Credit\] selection wise Card number should appear. **Reference**: * [https://prnt.sc/HHNFEJa6g-sn](https://prnt.sc/HHNFEJa6g-sn) * https://prnt.sc/kQdvEHUlBbFh
24554 | [App][UI][ServiceRequest][Card Reissue Request] Remove VAT, Service Charge, Amount, and Grand Total fields. | Bug | Rejected | 12/23/2024 02:36 PM | 12/24/2024 |  | 0.0 | Md. Shakhawat Hossain | Normal |  | NCC IB & Wallet | #### Reference:
24555 | [App][Functional][ServiceRequest][BAYD] User can select passed time during BAYD registration | Bug | Closed | 12/23/2024 02:40 PM | 12/24/2024 | 0.5h | 0.5 | Emam Hasan Bijoy | Normal |  | NCC IB & Wallet | Steps: 1. Go to Other services &gt; BAYD Registration 2. During registration, observe that user select already passed time
24556 | [App][UI][ServiceRequest][BAYD] Date and Time not showing in success page | Bug | Closed | 12/23/2024 02:51 PM | 12/30/2024 |  | 0.5 | Pronab Kumar Halder | Normal |  | NCC IB & Wallet | Steps: 1. Go to Other services &gt; BAYD Registration 2. Do a registration 3. On the success page, observe that Date and Time not showing. https://prnt.sc/9H0Eyh7BHbPp
24557 | [App][UI][ServiceRequest][BAYD] Placeholder text should be "Enter Mobile Number" | Bug | Closed | 12/23/2024 02:53 PM | 12/24/2024 | 0.5h | 0.5 | Emam Hasan Bijoy | Normal |  | NCC IB & Wallet | Steps: 1. Go to Other services &gt; BAYD Registration 2. Observe that field name is "Mobile Number" but placeholder text is "Enter Phone Number". Placeholder text should be "Enter Mobile Number" https://prnt.sc/awCEjIXgdn\_s
24559 | [App][Functional][ServiceRequest][BAYD] Manage BAYD Preferences and Cancel BAYD Registration not implemented in app | Bug | Closed | 12/23/2024 02:58 PM | 12/24/2024 |  | 0.25 | Md. Yasir Arafat Nayem | Blocker |  | NCC IB & Wallet
24561 | [Admin][Functional][ServiceRequest][BAYD] Filter with "Service Date" not working | Bug | Closed | 12/23/2024 03:00 PM | 12/31/2024 |  | 2.0 | Abir Hossain | Blocker |  | NCC IB & Wallet | Steps: 1. Go to Admin 2. Go to Service Request &gt;BAYD Registration 3. Filter with Service Date 4. Observe that data is not showing
24567 | [App][Functional][ServiceRequest][Card Reissue Request] Requests aren't displayed in the Service Request History page. | Bug | Closed | 12/23/2024 03:09 PM | 12/24/2024 |  | 0.25 | Md. Shakhawat Hossain | Normal |  | NCC IB & Wallet | **Reference**:
24570 | [Admin][Functional][ServiceRequest][BAYD] BAYD Request details showing wrong field name | Bug | Closed | 12/23/2024 03:17 PM | 12/30/2024 |  | 0.5 | Pronab Kumar Halder | Blocker |  | NCC IB & Wallet | Steps: 1. Go to Admin 2. Go to Service Request &gt;BAYD Registration 3. Go to details of a request 4. Observe that in some fields 'Delivery Address' is written. What is the delivery address? During registration through app, there was no filed call 'Delivery Address" https://prnt.sc/sInlIJRcZlUe
24571 | [Admin][Dev][Functional][ServiceRequest][BAYD] Notification/ Email isn't appear for submitting a request, Approve request, Reject request and Cancel reqquest | Bug | Closed | 12/23/2024 03:19 PM | 12/29/2024 |  | 1.0 | MD Sadman Sakib | Normal |  | NCC IB & Wallet
24575 | [App][UI][ServiceRequest][Card Reissue Request]Remove Product Type and Phone Number from the filter options. | Bug | Closed | 12/23/2024 03:51 PM | 12/30/2024 | 0.5h | 0.5 | Mostafijur Rahman | Normal |  | NCC IB & Wallet | **Reference**:
24577 | [App][Functional][ServiceRequest][Cheque Status Enquiry] Instead of showing status of the cheque, it is initiating a request | Bug | Closed | 12/23/2024 03:58 PM | 12/30/2024 | 0.1h | 0.1 | Mostafijur Rahman | Blocker |  | NCC IB & Wallet | Steps: 1. Go to Admin 2. Go to Service Request &gt; Cheque Status Enquiry 3. Enter the account number and cheque number. 4. Click on 'Next; button 5. Observe that Instead of showing status of the cheque, it is initiating a request
24579 | [Admin][Functional][ServiceRequest][Cheque Status Enquiry] Admin should only View Cheque Status Enquiries | Bug | Closed | 12/23/2024 04:00 PM | 12/31/2024 |  | 11.0 | Pronab Kumar Halder | High |  | NCC IB & Wallet | Steps: 1. Go to Admin 2. Go to Service Request &gt; Cheque Status Enquiry 3. As per the requirement, admin user should only View Cheque Status Enquiries but admin can update, approve, cancel request
24580 | [Dev][App][ServiceRequest][Card Upgrade/Downgrade] Requested Data Not Displayed on Service Request History Page | Bug | Closed | 12/23/2024 04:22 PM |  |  | 0.25 | Md. Shakhawat Hossain | High |  | NCC IB & Wallet | **Environment:** Dev **Device:** Samsung F23 **Platform:** App **Steps to Reproduce:** * Go to the Request Card Upgrade/Downgrade page * Create a valid request * Now go to the Service Request History page * Select Request Type Card Upgrade/ downgrade * Now observe the data/list **Actual Result:** Requested Data Not Displayed on Service Request History Page **Expected Result:** Should show the all requested data
24586 | [Dev][App][ServiceRequest][Card Upgrade/Downgrade] The user is not getting any notification | Bug | Closed | 12/23/2024 04:28 PM | 12/29/2024 |  | 1.0 | MD Sadman Sakib | Normal |  | NCC IB & Wallet | _**Note: This issue is applicable for approval, rejection and other status**_ **Environment:** Dev **Device:** Samsung F23 **Platform:** App **Steps to Reproduce:** * Go to the Request Card Upgrade/Downgrade page * Create a valid request * Now observe the notification section **Actual Result:** The user is not getting any notification **Expected Result:** The user should receive all notifications as per the requirement
24588 | [Dev][API][ServiceRequest][Card Upgrade/Downgrade] The user is not getting any SMS or Email | Bug | Closed | 12/23/2024 04:30 PM | 12/31/2024 |  | 4.0 | Pronab Kumar Halder | Normal |  | NCC IB & Wallet | _**Note: This issue is applicable for approval, rejection and other status**_ **Environment:** Dev **Device:** Samsung F23 **Platform:** App **Steps to Reproduce:** * Go to the Request Card Upgrade/Downgrade page * Create a valid request * Now observe the notification section **Actual Result:** The user is not getting any SMS or Email **Expected Result:** The user should receive all SMS or Email as per the requirement
24618 | [Dev][Admin][ServiceRequest][Card Upgrade/Downgrade] "Hold" Option Missing in Status Dropdown | Bug | Closed | 12/23/2024 04:36 PM | 12/30/2024 |  | 0.5 | Pronab Kumar Halder | Normal |  | NCC IB & Wallet | **Environment:** Dev **Browser :** Chrome **Platform:** Admin **Steps to Reproduce:** * Go to the Request Card Upgrade/Downgrade page * Click on the Status dropdown * Now observe the dropdown list **Actual Result:** "Hold" Option Missing in Status Dropdown **Expected Result:** Should show hold option and also functional
24621 | [Dev][Admin][ServiceRequest][Card Upgrade/Downgrade] [Filter] The user able to select future date | Bug | Closed | 12/23/2024 04:46 PM |  |  | 0.0 | Md Mehedi Hasan Arif | Normal |  | NCC IB & Wallet | **Environment:** Dev **Browser:** Chrome **Platform:** Admin **Steps to Reproduce:** * Go to the Request Card Upgrade/Downgrade page * Open the calendar for From Date &amp; To date * Now observe the calendar **Actual Result:** The user able to select future date **Expected Result:** The user should not able to select future date
24622 | [Dev][Admin][ServiceRequest][Card Upgrade/Downgrade][Filter] Missing Validation for "From Date" and "To Date" Selection | Bug | Closed | 12/23/2024 04:49 PM |  |  | 0.0 | Md Mehedi Hasan Arif | Normal |  | NCC IB & Wallet | **Environment:** Dev **Browser:** Chrome **Platform:** Admin **Steps to Reproduce:** * Go to the Request Card Upgrade/Downgrade page * Open the calendar for From Date &amp; To date * Now observe the calendar **Actual Result:** Missing Validation for "From Date" and "To Date" Selection **Expected Result:** Should add all kinds of validation
24623 | [Dev][Admin][ServiceRequest][Card Upgrade/Downgrade][Filter] Extra Input Fields "Product Type" and "Phone Number" Displayed | Bug | Closed | 12/23/2024 04:54 PM | 12/30/2024 |  | 0.5 | Pronab Kumar Halder | Normal |  | NCC IB & Wallet | **Environment:** Dev **Browser:** Chrome **Platform:** Admin **Steps to Reproduce:** * Go to the Request Card Upgrade/Downgrade page * Now observe the all filter input fields **Actual Result:** Extra Input Fields "Product Type" and "Phone Number" Displayed **Expected Result:** Should remove those extra fields
24624 | [Dev][Admin][ServiceRequest][Card Upgrade/Downgrade][Filter] "Request ID" Filter Input Field Missing | Bug | Closed | 12/23/2024 04:56 PM | 12/30/2024 |  | 0.5 | Pronab Kumar Halder | Normal |  | NCC IB & Wallet | **Environment:** Dev **Browser:** Chrome **Platform:** Admin **Steps to Reproduce:** * Go to the Request Card Upgrade/Downgrade page * Now observe the all filter input fields **Actual Result:** "Request ID" Filter Input Field Missing **Expected Result:** Should add "Request ID" Input Field for filter
24632 | [Dev][Admin][ServiceRequest][Card Upgrade/Downgrade] Remarks data missing on the Details page | Bug | Closed | 12/23/2024 05:03 PM |  |  | 0.0 | Md Mehedi Hasan Arif | Normal |  | NCC IB & Wallet | **Environment:** Dev **Browser:** Chrome **Platform:** Admin **Steps to Reproduce:** * Go to the Request Card Upgrade/Downgrade page * Click on the details of statuses such as "Hold," "Processing," or "Cancel." * Now observe the Details page **Actual Result:** Remarks data missing on the Details page **Expected Result:** Should show Remarks data on the Details page
24637 | [App][Functional][ServiceRequest][Request for different types of certificates] After selecting dropdown data, an error message appears. | Bug | Closed | 12/23/2024 05:22 PM | 12/30/2024 |  | 0.5 | Abir Hossain | Normal |  | NCC IB & Wallet
24732 | [Dev][App][ServiceRequest][Request Supplementary Card] The user is not getting any notification | Bug | Closed | 12/24/2024 10:49 AM | 01/05/2025 | 1h | 0.2 | Pronab Kumar Halder | Normal |  | NCC IB & Wallet | _**Note: This issue is applicable for approval, rejection and other status**_ **Environment:** Dev **Device:** Samsung F23 **Platform:** App **Steps to Reproduce:** * Go to the Request Supplementary Card page * Create a valid request * Now observe the notification section **Actual Result:** The user is not getting any notification **Expected Result:** The user should receive all notifications as per the requirement
24733 | [Dev][App][ServiceRequest][Request Supplementary Card] Cancel Button Navigates to Incorrect Page | Bug | Rejected | 12/24/2024 10:57 AM |  |  | 0.0 | Md. Shakhawat Hossain | Normal |  | NCC IB & Wallet | **Environment:** Dev **Device:** Samsung F23 **Platform:** App **Steps to Reproduce:** * Go to the Request Supplementary Card page * Input valid data and click on the next button * Click on the Cancel button * Now observe that after clicking on the cancel button, the system is redirected to the sidebar **Actual Result:** Cancel Button Navigates to Incorrect Page **Expected Result:** When the user clicks the "Cancel" button, they should be navigated back to the appropriate previous page
24741 | [Dev][App][ServiceRequest][Request Supplementary Card] Requested Data Not Displayed on Service Request History Page | Bug | Closed | 12/24/2024 11:10 AM |  |  | 0.25 | Md. Shakhawat Hossain | High |  | NCC IB & Wallet | **Environment:** Dev **Device:** Samsung F23 **Platform:** App **Steps to Reproduce:** * Go to the **Request Supplementary Card** page * Create a valid request * Now go to the Service Request History page * Select Request Supplementary Card from the dropdown * Now observe the data/list **Actual Result:** Requested Data Not Displayed on Service Request History Page **Expected Result:** Should show all the requested data
24744 | [Dev][Admin][ServiceRequest][SUPPLEMENTARY CARD REQUEST][Filter] "Request ID" Filter Input Field Missing | Bug | Closed | 12/24/2024 12:01 PM | 12/30/2024 |  | 0.5 | Pronab Kumar Halder | Normal |  | NCC IB & Wallet | **Environment:** Dev **Browser:** Chrome **Platform:** Admin **Steps to Reproduce:** * Go to the **SUPPLEMENTARY CARD REQUEST** page * Now observe all the input fields **Actual Result:** "Request ID" Filter Input Field Missing **Expected Result:** Should add "Request ID" Input Field for filter
24745 | [Dev][Admin][ServiceRequest][SUPPLEMENTARY CARD REQUEST][Filter] Few text showing Lowercase | Bug | Closed | 12/24/2024 12:06 PM | 12/30/2024 |  | 0.5 | Pronab Kumar Halder | Low |  | NCC IB & Wallet | **Environment:** Dev **Browser:** Chrome **Platform:** Admin **Steps to Reproduce:** * Go to the **SUPPLEMENTARY CARD REQUEST** page * Now observe all the input field's label **Actual Result:** Few text showing Lowercase **Expected Result:** Should show uppercase
24746 | [Dev][Admin][ServiceRequest][SUPPLEMENTARY CARD REQUEST] Date of Birth Column missing | Bug | Closed | 12/24/2024 12:08 PM | 12/30/2024 |  | 0.5 | Pronab Kumar Halder | Normal |  | NCC IB & Wallet | **Environment:** Dev **Browser:** Chrome **Platform:** Admin **Steps to Reproduce:** * Go to the **SUPPLEMENTARY CARD REQUEST** page * Now observe all the columns **Actual Result:** Date of Birth Column missing **Expected Result:** Should show Date of Birth Column
24747 | [Dev][Admin][ServiceRequest][SUPPLEMENTARY CARD REQUEST] "supply CardHolder Name" showing instead of "Supply Cardholder Name" | Bug | Closed | 12/24/2024 12:11 PM | 12/30/2024 |  | 0.5 | Pronab Kumar Halder | Normal |  | NCC IB & Wallet | _**Note: This issue exists in the filter section**_ **Environment:** Dev **Browser:** Chrome **Platform:** Admin **Steps to Reproduce:** * Go to the **SUPPLEMENTARY CARD REQUEST** page * Now observe the columns **Actual Result:** "supply CardHolder Name" showing instead of "Supply Cardholder Name" **Expected Result:** The column name should be "Supply Cardholder Name"
24749 | [Dev][Admin][ServiceRequest][SUPPLEMENTARY CARD REQUEST] "Hold" Option Missing in Status Dropdown | Bug | Closed | 12/24/2024 12:13 PM | 12/30/2024 |  | 0.5 | Pronab Kumar Halder | Normal |  | NCC IB & Wallet | **Environment:** Dev **Browser:** Chrome **Platform:** Admin **Steps to Reproduce:** * Go to the **SUPPLEMENTARY CARD REQUEST** page * Click on the Status dropdown * Now observe the dropdown list **Actual Result:** "Hold" Option Missing in Status Dropdown **Expected Result:** Should show hold option and also functional
24752 | [Dev][Admin][ServiceRequest][SUPPLEMENTARY CARD REQUEST] Date of Birth filter not working and front mismatch | Bug | Closed | 12/24/2024 12:27 PM | 12/30/2024 |  | 0.5 | Pronab Kumar Halder | Normal |  | NCC IB & Wallet | _**Note: The front issue exists on the details page**_ **Environment:** Dev **Browser:** Chrome **Platform:** Admin **Steps to Reproduce:** * Go to the **SUPPLEMENTARY CARD REQUEST** page * Input a valid date of birth * Now observe the list **Actual Result:** The date of Birth filter not working and the front mismatch Details page: **Expected Result:** The filter should work and the Front size should be the same
24757 | [Dev][Admin][ServiceRequest][SUPPLEMENTARY CARD REQUEST] Remarks data missing on the Details page | Bug | Closed | 12/24/2024 12:35 PM |  |  | 0.0 | Md Mehedi Hasan Arif | Normal |  | NCC IB & Wallet | **Environment:** Dev **Browser:** Chrome **Platform:** Admin **Steps to Reproduce:** * Go to the **SUPPLEMENTARY CARD REQUEST** page * Click on the details of statuses such as "Hold," "Processing," or "Cancel." * Now observe the Details page **Actual Result:** Remarks data missing on the Details page **Expected Result:** Should show Remarks data on the Details page
25407 | [Admin][Functional][ServiceRequest][Cheque Status Enquiry] Admin should only View Cheque Status Enquiries | Bug | Closed | 01/01/2025 05:16 PM | 01/01/2025 | 3h | 3.0 | Md Mehedi Hasan Arif | High |  | NCC IB & Wallet | Steps: 1. Go to Admin 2. Go to Service Request &gt; Cheque Status Enquiry 3. As per the requirement, admin user should only View Cheque Status Enquiries but admin can update, approve, cancel request
25556 | [WEB][UAT][W53RE][Other- One time Pay] "Next" Button Remains Disabled After Filling All Required Fields with Valid Data | Bug | Closed | 01/02/2025 10:20 AM | 01/02/2025 | 1h | 1.0 | Md Mehedi Hasan Arif | High |  | NCC IB & Wallet | **Environment:** UAT **Browser:** Chrome **Platform:** Web **Steps to Reproduce:** * Go to the Sidebar or Dashboard * Click on the **Fund Transfer** menu * Click on the Other Bank Account Submenu * Go to the One-time pay page * Input valid data for all the required fields * Now observe the Next button **Actual Result:** "Next" Button Remains Disabled After Filling All Required Fields with Valid Data **Expected Result:** The "Next" button should be enabled and the user should be able to process the next step